## Sheet1
|  | Play Notes |  |  | Tasks Accomplished
Date | Change Log | Successes/Issues | Proposed Solutions | Next Steps | Cameron
2021-10-16 | Game Created. | Successes: Game was created and the basic systems are functional.The start/stop button makes me chuckle. Issues: Not all of the calculations are functional and several features are missing | Keep on keeping on | Finish the calculations work so that the game can be played and provide feedback for the user. | I did it all.
2021-10-20 | Updated the calcuations and variables that determine the values that control various aspects of the game. Most notably the Total Score variable, which combines several other values. Some minor visual elements are added and debug elements are moved to enable toggling. | The game is not terribly fun, but all major functionality is present. | Multimedia will help, but I think having some kind of tactile feedback for interactions will be more important. | Need to add leveling system and multimedia immediately, work on second game interaction after. Also, some of the variables are calculated obtusely. I can make them better.
2021-10-27 | Added basic Game 2 Cleaned up events into appropriate sheets so they can be called based on the game being played and global conditions | Was able to separate events and create a new subgame without needing to recreate or duplicating events. Should allow for easier addition of future subgames and features But the event sheets are still messy and the games are still very simple. | I can clean up the event sheets pretty easily. More broadly, setting all games to a universal random seed would further simplify how each subgame interacts with the larger game. | <--- The items in the proposed solutions column are immediate next steps. After that, developing the actual games further and adding secondary mechanics, like music | x
2021-11-04 | - Added additional hotspots - Added feedback sounds - Removed dev toggle - Change scoring system - Removed Game 1 (for now) | Something happened and I my control variables (specifically one I called sceneRandrom) stopped updating entirely after some trivial change.After a while of troubleshooting, I had to recreate Game 2. | Variables seemed to start working again after completely closing and reloading Construct 3. So I.guess more frequent saves? | Figure out game theme and make additional games. There also needs to be a floor for click scores.